## Gantt Chart
GANTT CHART GROUP 03 |  |  |  | Valerio De Luca, Mattero Mastromauro, Paolo Massacci, Siyi Wang
COURSE |  | Design and Robotics |  |  |  |  | PROJECT TITLE | [8 empty] | CamaLele
EDITION |  | 11th |  |  |  |  | DATE | [8 empty] | 2023-03-07
WBS NO. | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [20 empty] | PHASE TWO | [20 empty] | PHASE THREE | [20 empty] | PHASE FOUR
[7 empty] | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12
 | time axis 2023-03-07 to 2023-05-29
1 | Phase 1: Discover
1.1 | Create a Gantt chart | Valerio | 2023-03-07 | 2023-03-07 | 0 | 100% | bar: 2023-03-07
1.2 | Decide the animal to associate | All | 2023-03-07 | 2023-03-10 | 3 | 100% | bar: 2023-03-07 to 2023-03-10
1.3 | Assign roles | All | 2023-03-10 | 2023-03-10 | 0 | 100% | bar: 2023-03-10
1.4 | Make Moodboard | Siyi | 2023-03-11 | 2023-03-14 | 3 | 100%
1.5 | Make Storyboard | Siyi | 2023-03-14 | 2023-03-17 | 3 | 100%
1.6 | Decide on robot's characteristics | All | 2023-03-17 | 2023-03-24 | 7 | 100% | bar: 2023-03-17 to 2023-03-24
1.7 | Think of possible electronics | Matteo | 2023-03-18 | 2023-03-24 | 6 | 100%
1.8 | Bill of materials | Matteo | 2023-03-24 | 2023-03-24 | 0 | 100%
1.9 | Supegroup meeting | Valerio | 2023-03-24 | 2023-03-24 | 0 | 100%
1,10 | Make prototypes | All | 2023-03-24 | 2023-03-27 | 3 | 100%
1,11 | Creat a presentaion template | Siyi | 2023-03-27 | 2023-03-27 | 0 | 100%
2 | Phase 2: Define
2.1 | Reshape eyes | Paolo | 2023-03-28 | 2023-04-08 | 10 | 100%
2.2 | Sketch a draft of structure | Paolo & Matteo | 2023-04-01 | 2023-04-06 | 5 | 100%
2.3 | Initial code setup | Valerio | 2023-04-02 | 2023-04-09 | 7 | 100%
2.4 | Design a draft of the circuit | Matteo | 2023-04-03 | 2023-04-10 | 7 | 100%
2.5 | Code for basic servo movements | Valerio & Matteo | 2023-04-06 | 2023-04-13 | 7 | 100%
2.6 | Design of the shape | Paolo | 2023-04-07 | 2023-04-17 | 10 | 100%
2,7 | Order electronic components | Matteo | 2023-04-08 | 2023-04-15 | 7 | 100%
2.8 | First model of the tail | Siyi | 2023-04-10 | 2023-04-17 | 7 | 100%
2.9 | State diagram of the emotions | Valerio | 2023-04-14 | 2023-04-14 | 0 | 100%
2,10 | Supegroup meeting | Valerio | 2023-04-18 | 2023-04-18 | 0 | 100%
3 | Phase 3: Develop
3.1 | Model neck | Paolo | 2023-04-18 | 2023-04-25 | 7 | 100%
3.2 | Model chest | Paolo | 2023-04-18 | 2023-04-25 | 7 | 100%
3.3 | Unwrap eyes and eyelids | All | 2023-04-18 | 2023-05-01 | 13 | 100%
3,4 | Manual controller | Valerio | 2023-04-20 | 2023-04-30 | 10 | 100%
3.5 | 3D print skeleton | Paolo & Siyi | 2023-04-24 | 2023-05-03 | 9 | 100%
3.6 | Printing of the components | Paolo | 2023-04-25 | 2023-05-01 | 6 | 100%
3,7 | First tail prototype | Siyi | 2023-04-25 | 2023-05-01 | 6 | 100%
3,8 | Circuit implementation on breadboard | Matteo | 2023-05-01 | 2023-05-06 | 5 | 100%
3,9 | Tuning of the motors | Valerio & Matteo | 2023-05-01 | 2023-05-08 | 7 | 100%
3,10 | Tuning of basic movements | Valerio & Matteo | 2023-05-01 | 2023-05-08 | 7 | 100%
3,11 | Prototype for chest | Paolo & Matteo | 2023-05-02 | 2023-05-05 | 3 | 100%
3,12 | Prototype for neck | Paolo & Matteo | 2023-05-02 | 2023-05-05 | 3 | 100%
3,13 | Supergroup meeting | Valerio | 2023-05-04 | 2023-05-04 | 0 | 100%
3,14 | First components assembly | Matteo | 2023-05-05 | 2023-05-05 | 0 | 100%
3,15 | Fix power supply problems | Valerio & Matteo | 2023-05-06 | 2023-05-13 | 7 | 100%
3,16 | Implementation of sad emotion | Valerio | 2023-05-06 | 2023-05-08 | 2 | 100%
3,17 | Implementation of angry emotion | Valerio | 2023-05-06 | 2023-05-08 | 2 | 100%
3,18 | Implementation of shocked emotion | Valerio | 2023-05-06 | 2023-05-08 | 2 | 100%
3,19 | Assemble the robot | All | 2023-05-08 | 2023-05-08 | 1 | 100%
3,20 | Dual core task managing | Valerio | 2023-05-08 | 2023-05-08 | 1 | 100%
4 | Phase 4: Deliver
4,1 | Printing of reduced eyes and eyelids | Paolo | 2023-05-09 | 2023-05-10 | 1 | 100%
4,2 | Printing of the base | Paolo | 2023-05-10 | 2023-05-10 | 0 | 100%
4,3 | Polipropilene tail creation | Siyi | 2023-05-10 | 2023-05-18 | 8 | 100%
4,4 | Supergroup discussion | Valerio | 2023-05-11 | 2023-05-13 | 2 | 100%
4,5 | Model of the tail connection | Paolo & Matteo | 2023-05-11 | 2023-05-14 | 3 | 100%
4,6 | Reprint wrong components | Paolo | 2023-05-11 | 2023-05-20 | 9 | 100%
4,7 | Mp3 connection | Matteo | 2023-05-14 | 2023-05-17 | 3 | 100%
4,8 | Supergroup meeting | Valerio | 2023-05-15 | 2023-05-15 | 0 | 100%
4,9 | Painting components | All | 2023-05-15 | 2023-05-18 | 3 | 100%
4,10 | Message buffer with priority | Valerio | 2023-05-15 | 2023-05-22 | 7 | 100%
4,11 | Code debugging | Valerio | 2023-05-15 | 2023-05-22 | 7 | 100%
4,12 | Mp3 code setup | Valerio | 2023-05-17 | 2023-05-17 | 0 | 100%
4,13 | Text-to-speech generation | Valerio | 2023-05-18 | 2023-05-18 | 0 | 100%
4,14 | Select audio for emotions | Valerio | 2023-05-18 | 2023-05-21 | 3 | 100%
4,15 | Make final tail move correctly | Matteo | 2023-05-18 | 2023-05-21 | 3 | 100%
4,16 | Implementation of cautious emotion | Valerio & Siyi | 2023-05-18 | 2023-05-18 | 0 | 100%
4,17 | Implementation of happy emotion | Valerio & Siyi | 2023-05-19 | 2023-05-19 | 0 | 100%
4,18 | Implementation of annoyed emotion | Valerio & Siyi | 2023-05-20 | 2023-05-20 | 0 | 100%
4,19 | Implementation of idle state | Valerio | 2023-05-21 | 2023-05-21 | 0 | 100%
4,20 | Solder the circut | Matteo | 2023-05-19 | 2023-05-19 | 0 | 100%
4,21 | Slides for final presentation | Paolo | 2023-05-20 | 2023-05-22 | 2 | 100%
4,22 | Fix audio problems | Valerio | 2023-05-21 | 2023-05-22 | 1 | 100%
4,23 | Robot assembly | Matteo | 2023-05-21 | 2023-05-22 | 1 | 100%
4,24 | Simulation of final presentation | All | 2023-05-22 | 2023-05-22 | 0 | 100%
4,25 | Fix idle state | Valerio | 2023-05-23 | 2023-05-23 | 0 | 100%
4,26 | Last fixes between presentations | All | 2023-05-23 | 2023-05-23 | 0 | 100%